## Sheet1
Task/Activity | Status | Start Date | End Date | September | October | November | December | January | February | March | April
Topic selection and supervisor approval | Completed | 2025-10-09 | 16/09/2025
Requirement gathering and flow diagrams | Completed | 17/09/2025 | 30/09/2025
UI/UX design (figma prototypes) | Completed | 2025-01-10 | 25/10/2025
Proposal submission | Completed | 31/10/2025 | 31/10/2025
Sprint 1: Frontend development | Finalizing | 2025-01-11 | 15/12/2025
Sprint 2: Backend development and database setup | In Progress | 2026-01-01 | 31/01/2026
Sprint 3: Sytem integration,preview and payment module | Upcoming | 2026-01-02 | 20/02/2026
Sprint 4: Testing and debugging | Upcoming | 2026-01-03 | 20/03/2026
Final documentation and presentation | Upcoming | 21/03/2026 | 15/04/2026